## Sheet2
Budget
2017 Annual Compliance Outage | 90% Budget | 10% Contingency | Actual Budget
Kraft Mill Area | 2250000 | 250000 | 2500000
Recovery Boiler | 1305000 | 145000 | 1450000
Evaporators | 315000 | 35000 | 350000
Cooling Tower | 58500 | 6500 | 65000
Lime Kiln & Re-Causticizing Area | 1215000 | 135000 | 1350000
Total on A/F's for approval | 5188500 | 576500 | 5765000
Note:
The $2.5 MM for the Kraft Mill includes the ClO2 Re-boiler

## Sheet1
Budget | Plan

## Actual
| Equipment Down |  | Maint Begin |  | Maint Complete |  | Equipment Startup |  | Downtime
Area | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
PM1 | 1:00 am Tue | 1:12 am Tue | 8:00 am Tue | 8:00 am Tue | 8:00 pm Thu | 12:30 am Fri | 4:00 am Fri | 9:55 am Fri | 75:00 | 80:43
PM2 | 5:00 am Tue | 6:42 am Tue | 8:00 am Tue | 8:00 am Tue | 8:00 pm Thu | 9:00 am Fri | 4:00 am Fri | 12:00 pm Fri | 71:00 | 77:18
PM3 | 7:00 am Tue | 6:47 am Tue | 8:00 am Tue | 8:00 am Tue | 8:00 am Fri | 11:00pm Fri | 4:00 pm Fri | 11:05 pm fri | 81:00 | 88:18
PM4 | 4:00 am Tue | 9:40 pm Mon | 8:00 am Tue | 8:00 am Tue | 8:00 am Fri | 6:25 am Sat | 4:00 pm Fri | 11:00 am Sat | 84:00 | 109:20
PM5 | 11:00 pm Mon | 11:05 pm Mon | 8:00 am Tue | 8:00 am Tue | 4:00 pm Thu | 11:20pm Thu | 6:00 pm Thu | 2:03 am Fri | 67:00 | 74:58
[8 empty] | Average | 75:36 | 86:07
| Bowater |  | Contractors
Safety | First Aid | Recordable | First Aid | Recordable
| 3 | 1 | 2 | 1
Cost | Plan |  | Actual (Preliminary)
5008723
Work | Planned | Completed | Addon Scope Changes
| 724 | 698 | 41

## Detailed Schedule
Revision 0 |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
March 2019 Outage | Duration | Down | 2019-03-23 | 2019-03-24 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | Maint | Warm Up | In Service | Updated 01/19/19
| hours | Plan | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Comp | Plan | Plan | Comments/Opportunities
COLD MILL TARGET | bar: hours
Tissue Machine | hours: 48; Plan: 5pm Mon; Comp: 8am Mon; Plan: 4pm Mon
Warm 6 hrs
Pulp Dryer | hours: 138; Plan: 5pm Mon; Comp: 8am Tue; Plan: 4pm Tue; Plan: 4pm Tue
Warm 6 hrs
No. 4 Machine | hours: 54; Plan: 4am Mon; Comp: 8am Mon; Plan: 11am Mon
BKR 1008 - Stock Prep | hours: 14; Plan: 6am Mon
BKR 1506/2502 - LCR/HCR, | hours: 28; Plan: 6 am Wed
BKR 4006 - CR 48-3, CR 48-4 | hours: 40; Plan: 8 am Thur
Warm early
Kraft Mill
Chips Off to Bin | Plan: 8am Sat; Mon: Digester Inspection and Repair; Comp: 8am Sun; Plan: 8am Sun; Plan: 3pm Sun
Digester | Plan: 8pm Sat; Comp: 8am Sat; Plan: 5pm Sat; Plan: 3pm Sun
Brown Stock | Plan: 9pm Sat; Comp: 8am Sat; Plan: 8am Sat; Plan: 3pm Sun
Bleach Plant | Plan: 12pm Sun; Mon: D Tower Repair; Comp: 3am Mon; Plan: 3am Mon | Bleach Plant on D Tower Bypass March 16
Weak Liquor Flow Off | Plan: 8am Sun; Comp: 8am Sat; Plan: 3pm Sun
BKR 1503 Outage affects equipment in CR 52-1, -5, Chem Prep and CLO2 | hours: 14; Plan: 6am Tue
Recovery Boiler | Plan: 12am Sun; Mon: Recovery Compliance Outage; Comp: 12am Sun; Plan: 12am Sun; Plan: 12am Sun
Evaporators | Plan: 12am Sun; Comp: 12am Sun; Plan: 12am Sun; Plan: 12am Sun
Inc Bus 5 & Load Bus 5 - RB3 & Evaps | hours: 38; Plan: 8am Thu
Chip Prep | hours: NLL; Plan: 8am Fri; Plan: 5 pm Fri
BKR 3007 - Chip Screen & P&H Crane, Reclaimers | hours: 14; Plan: 6am Mon
BKR 2007 - NLL Drum | hours: 14; Plan: 6am Mon
| SLL | [13 empty] | 8a Thur
South Log Line - BKR 136 | hours: 38; Plan: 8am Thu
BKR 137, 2004, 3002, 4002 - Utilities area, turbines, demins - CR 28-1, 2, 3, 4, coal yard | hours: 38; Plan: 6am Tue
BKR 1004 - Technical building | hours: 8; Plan: 7am Tue
Facilities Building & Old Gwd | hours: 14; Plan: 6am Wed
Air Compressors | Plan: 2am Tue; Comp: 3pm Thu; Plan: 3pm Thu
Inc Bus 3, 4, 6 - TMP & PM5 air compressors | hours: 38; Plan: 6am Tue
Mill Water System | hours: 36; Plan: 2am Tue; Plan: 12pm Thu
Raw Water 1 | hours: 1; Plan: 8am Tue; Wed: South Booster Pump; Plan: 12pm Thu | Down 1 Hour to switch power source
Raw Water 2 | Plan: 10pm Fri
Effluent System
Steam System | Plan: 7pm Mon; Plan: 10pm Fri
BFB | Plan: 5pm Mon; Sat: FIRE IN BFB; Plan: 8pm Fri | Flame in PB1 & PB3 about 6:30a Thurs, PB2 @ 9:45a; BFB on line 9:00p Thurs
PB2 | Plan: 7pm Mon; Sat: FIRE IN PB2; Plan: 2pm Fri | Controlling job
Support process steam | Sat: SUPPORT PROCESS; Plan: 2am Sat
TG1 | Plan: 3pm Mon; Plan: 9am Sun
TG2 | Plan: 5pm Mon; Plan: 8am Sat
TG3 | Plan: 7pm Mon; Plan: 6am Sat
Fire Water System
Tick Lines Represent 8am of the Day Listed Above
No Process Steam
Note on Q2: Bowater Newsprint: Following Maintenance followup to Operations Meeting of 5-19-04

## Maintenance Critical Path
|  |  | 2004-06-19 | 2004-06-20 | 2004-06-21 | 2004-06-22 | 2004-06-23 | 2004-06-24 | 2004-06-25 | 2004-06-26 | Equipment | Critical Path
Revison 1 | Work Begins | Duration | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Available | Executed by | Critical Path Work
Chip Prep
TUBE BELT | Mon 8am | 60 Hrs | [8 empty] | Wed 8pm |  | Tube Belt rollers and Takeup Pulley/ B9 CTS Acc HD Pulley
NLL | Mon 8am | 105 Hrs | [8 empty] | Fri 5pm | Contractor | Power Feed Wear Plate Replacement
SLL | Mon 8am | 72 Hrs | [8 empty] | Thu 8am | Bow Maint | Tube Belt
No. 1 Machine | Tue 8am | 60 Hrs | [8 empty] | Thu 8pm | Contractor | Gear Train Repairs
No. 2 Machine | Tue 8am | 60 Hrs | [8 empty] | Thu 8pm | Contractor | Gear Train and Chest Repairs
No. 3 Machine | Tue 8am | 72 Hrs | [8 empty] | Fri 8am | Contractor | Tray Silo and Chest Repairs
No. 4 Machine | Tue 8am | 72 Hrs | [8 empty] | Fri 8am | Contractor | Gear Train and Press Section Repairs
No. 5 Machine | Tue 8am | 56 Hrs | [8 empty] | Thu 4pm | Bow Maint | Calendar Stack Replacement and Calendar Jacks
Finishing & Shipping | Tue 12pm | 52 Hrs | [8 empty] | Thu 4pm | Bow Maint | A & B Mill Belt and head Pulley Replacement
TMP Lines 1-4 | Tue 8am | 60 Hrs | [8 empty] | Thu 8am | Bow Maint | Isolation valve Replacements (11 Valves)
Lines 5-6 | Tue 8am | 60 Hrs | [8 empty] | Thu 8am | Bow Maint | See Above
Line 7 - 8 | Mon 8pm | 60 Hrs | [8 empty] | Thu 8am | Bow Maint | See Above/Twin Screw Drainer
Recycle | Mon 8am | 120 Hrs | [8 empty] | Fri 8am | Contractor | Project
Pulp Dryer | Mon 8am | 120 hrs | [8 empty] | Sat 8am | Contractor | Former Replacement
Kraft Mill | Tue 8am | 72 Hrs | [8 empty] | Thu 3pm | Contractor | D100 FRP Repairs and Bleach Plant Feed Tank Replacement
Decker Repair has Become the Controlling Job
Steam System | Tue 12pm | 32 Hrs | [8 empty] | Wed 8pm | Contractor | Water And Steam Work (See Below)
Air System Repairs | Tue 8pm | 12 Hrs | [8 empty] | Wed 8am | Contractor | Air Leak in Old Kraft Mill Area off Main Header
Water Systems | Tue 12 noon | 36 Hrs | [8 empty] | Wed 8pm | Contractor | Mill Water Line Under Turbine Floor/Mill water Booster Pump Repairs
No. 3 Recovery | Fri 8pm | 168 Hrs | [8 empty] | Fri 8pm | Contractor | Annual Outage
Evaporators | [10 empty] | Fri 8am | Contractor | Repair of the First Effect
Power Outages
#1 Raw Water Power | Wed 8am | 12Hrs
#2 Raw Water | Tue 12Noon | 12 hrs | [8 empty] | Wed 12 Mid
#3 PM Power Dist | Tue 8am | 12 Hrs
Filter Plant Power | Thu 8am | 12 Hrs
Causticizing | Sun 8pm | 136 Hrs | [8 empty] | Sat 8am | Contractor | North GL Clarifier
Lime Kiln | Sun 8am | 160 Hrs | [8 empty] | Sat 8am | Contractor | Clean Out and Repair
Incinerator | Tue 8pm | 72 Hrs | [8 empty] | w/Evaps | Contractor | Annual Outage
850# Steam | Tue 12pm | 32 Hrs | [8 empty] | Wed 8pm | Contractor | Valve Rebuilds and Valve Packing Replacement
180# Steam | Tue 12pm | 32 Hrs | [8 empty] | Wed 8pm | Contractor | See Above
150# Steam | Tue 12pm | 32 Hrs | [8 empty] | Wed 8pm | Contractor | See Above
50# Steam | Tue 12pm | 32 Hrs | [8 empty] | Wed 8pm | Contractor | See Above
Effluent Clarifier | Wed 8am | 12hrs | [8 empty] | Wed 8pm | Contractor | Inspection of Waste Lift Box During Low Flow By Diver
Sludge Plant | As Needed | No Outage Work | [8 empty] | As Needed
No. 1 Power | As Needed | No Outage Work | [8 empty] | As Needed
No. 2 Power | As Needed | No Outage Work | [8 empty] | As Needed
No. 3 Power | As Needed | No Outage Work | [8 empty] | As Needed
BFB | As Needed | No Outage Work | [8 empty] | As Needed
No. 1 Turbine | As Needed | No Outage Work | [8 empty] | As Needed
No. 2 Turbine | Wed 8am | [9 empty] | Wed 8pm | Contractor | Valves to be Replaced
No. 3 Turbine | As Needed | No Outage Work | [8 empty] | As Needed
end

## Production Impact
Scheduled Outage Duration |  |  |  | [Hours] |  |  |  | Scheduled | Actual |  | Cold Mill Outage Production Impact
| Sun | Mon | Tue | Wed | Thu | Fri | Sat | HOURS DOWN
| 2004-06-20 | 2004-06-21 | 2004-06-22 | 2004-06-23 | 2004-06-24 | 2004-06-25 | 2004-06-26
No 1 Machine |  | 6 | 24 | 24 | 21 |  |  | 75 | 80.9167 | -5.9167
No 2 Machine |  | 2 | 24 | 24 | 21 |  |  | 71 | 77.7 | -6.7
No 3 Machine |  | 0 | 24 | 24 | 24 | 9 |  | 81 | 88.5833 | -7.5833
No 4 Machine |  | 3 | 24 | 24 | 24 | 9 |  | 84 | 105.3333 | -21.3333
No 5 Machine |  | 8 | 24 | 24 | 11 |  |  | 67 | 74.9167 | -7.9167
Pulp Dryer |  | 23 | 24 | 24 | 24 | 24 | 9 | 128 | 133.6667 | -5.6667
Scheduled Tonnes Lost
No 1 Machine |  | 77.5 | 310 | 310 | 271.25 | 0
No 2 Machine |  | 23.8333 | 286 | 286 | 250.25 | 0
No 3 Machine |  | 0 | 372 | 372 | 372 | 139.5
No 4 Machine |  | 49.75 | 398 | 398 | 398 | 149.25
No 5 Machine |  | 204 | 612 | 612 | 280.5 | 0
|  | -355.0833 | -1978 | -1978 | -1572 | -288.75
Cumulative Paper |  | -355.0833 | -2333.0833 | -4311.0833 | -5883.0833 | -6171.8333 | -6171.8333
Pulp Dryer |  | -423.3533 | -441.76 | -441.76 | -441.76 | -441.76 | -165.66
Cumulative Pulp |  | -423.3533 | -865.1133 | -1306.8733 | -1748.6333 | -2190.3933 | -2356.0533
Actual Outage Duration
No 1 Machine |  | 5.9167 | 24 | 24 | 24 | 3 |  | 80.9167
No 2 Machine |  | 0.7 | 24 | 24 | 24 | 5 |  | 77.7
No 3 Machine |  | 0.58333 | 24 | 24 | 24 | 16 |  | 88.5833
No 4 Machine |  | 9.3333 | 24 | 24 | 24 | 24 | 0 | 105.3333
No 5 Machine |  | 7.9167 | 24 | 24 | 19 | 0 |  | 74.9167
Pulp Dryer | 6.9167 | 24 | 24 | 24 | 24 | 24 | 13.6667 | 133.6667
Actual Tonnes Lost
No 1 Machine |  | 76.4236 | 310 | 310 | 310 | 38.75 | 0
No 2 Machine |  | 8.3417 | 286 | 286 | 286 | 59.5833 | 0
No 3 Machine |  | 9.0417 | 372 | 372 | 372 | 248 | 0
No 4 Machine |  | 154.7778 | 398 | 398 | 398 | 398 | 0
No 5 Machine |  | 201.875 | 612 | 612 | 484.5 | 0 | 0
|  | -450.4597 | -1978 | -1978 | -1850.5 | -744.3333 | 0
Cumulative Paper |  | -450.4597 | -2428.4597 | -4406.4597 | -6256.9597 | -7001.2931 | -7001.2931
Pulp Dryer | -127.3128 | -441.76 | -441.76 | -441.76 | -441.76 | -441.76 | -251.5578
Cumulative Pulp | -127.3128 | -569.0728 | -1010.8328 | -1452.5928 | -1894.3528 | -2336.1128 | -2587.6706
Paper v Plan |  | -95.3764 | -95.3764 | -95.3764 | -373.8764 | -829.4597 | -829.4597
Pulp v Plan | -127.3128 | -145.7194 | -145.7194 | -145.7194 | -145.7194 | -145.7194 | -231.6172
Total var from Plan | -127.3128 | -241.0958 | -241.0958 | -241.0958 | -519.5958 | -975.1792 | -1061.0769
Production Rate [MT/24 hours]
No 1 Machine | 310
No 2 Machine | 286
No 3 Machine | 372
No 4 Machine | 398
No 5 Machine | 612
Pulp Dryer | 441.76